## CAUTIoN Strategy
General Directorate of Infection Prevention and Control in Healthcare Facilities (GDIPC) - CAUTIoN STRATEGY
VISION: To eliminate CAUTI in national healthcare facilities by the end of the year 2025
MISSION: To enhance knowledge and practice related to the updated evidence-based bundles of interventions for the prevention of catheter-associated urinary tract infection (CAUTI) among all healthcare professionals in all national healthcare facilities.
GOAL: To reduce the current national CAUTI rate by 50% in all national healthcare facilities, starting from March 2023 to March 2025 (3 years period).
CAUTIoN to CAUTI (C 2 C - 0.5/1000 urinary catheter days)
NO | COMPONENT | GAP ANALYSIS | STRATEGIC GOAL | STRATEGIC OBJECTIVE | ACTIVITY | TASK & DUTY |  |  | RESPONSIBILITY | [8 empty] | TIMELINE (Quartely) | [11 empty] | M/E MECHANISM & TOOL | KPIs (Indicator) | RELEVANCY TO RATE REDUCTION |  | INTERVENTION LEVEL (IL)
[6 empty] | METHOD | PLACE | DURATION | HOSPITAL |  |  | REGION |  | GDIPC |  | MOH DEPT | PARTNER | 2023 |  |  |  | 2024 |  |  |  | 2025 | [5 empty] | HIGH | LOW
[9 empty] | ICU | IPC | ADM | RHD | CLUSTER | SURVEILLANCE PROGRAM | STRATEGY TEAM |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Leadership and Governance | 1. Failure to recognize the importance of reaching lower CAUTI Rates | 1. To improve awareness of leaders, administrators, and decision-makers about CAUTIoN and its impacts on the LOS, lowering the cost, and reducing morbidity & mortality consequently | To let Leaders and decision - makers to be fully aware of CAUTI reduction, its effects in shortening the LOS, lowering the costs and reducing the morbidity and mortality | Give an orientation to the targeted leaders and decision - makers on CAUTIoN Strategy and their roles & responsibilities in supporting the strategy | Online meeting | GDIPC | 1 day | [21 empty] | Meeting minutes | Number of the awarded and supportive leaders and decision - makers per Total number of the leaders and decision - makers x 100% |  |  | All Zones | bar: 2024 1; 2025 1
|  | 2. Lack of awareness of staff on CAUTI Prevention |  |  | Plan and execute campaigns to raise the awareness and motivate the HCWs | Plan of the campaign | GDIPC | 3 weeks | [7 empty] | Internal Communication | Interested companies | [12 empty] | A report of the campaign |  |  |  | All Zones | bar: 2024 1; 2025 1
|  | 3. Lack of awareness of leaders and decision makers on CAUTI Prevention |  |  | Assess the level of awareness of the leaders and decision makers | Survey e.g questionnaire/interview | GDIPC / Hospitals | 1 month | [21 empty] | Survey / Study's results and recommendations |  |  |  | Black & Red | bar: 2023 4; 2024 4; 2025 4
|  | 4. Lack of motivation (success stories are not encouraged) | 2. To construct evidence based best practices for effective implementation of CAUTIoN in national healthcare facilities |  | Use C2C Initiative as an encouragement tool for both the leaders & HCWs | CAUTI Out of Nation (C2C) competition | GDIPC/ Hospitals | 01/3 - 31/12/2023 | [7 empty] | Internal Communication | Interested companies | [12 empty] | C2C Final Report |  |  |  | Black & Red | bar: 2023 2 to 2023 4
|  | 5. No planned strategy to reduce CAUTI rates |  |  | Prepare to launch CAUTIoN Strategy | Meetings | GDIPC | 1 month | [8 empty] | Interested companies | [12 empty] | Brainstorming |  |  |  | All Zones
[5 empty] | Launch CAUTIoN Strategy | Event for CAUTIoN Strategy | GDIPC | 1 day | [7 empty] | Internal Communication | Interested companies | [12 empty] | Invitations |  |  |  | All Zones
2 | Urinary Catheter Insertion & Maintenance Supplies | 1. Supplies Shortage (Urinary catheter kits, PPE, Urine bags, Single used gels and others) | To maintain effective chain of supplies in national healthcare facilities for proper urinary catheter insertion and maintenance practices. | To have adequate supplies (Quantity and Quality) for proper urinary catheter insertion and maintainance practices in national healthcare facilities. | Prepare a list of actually available urinary catheter supplies accompanied with codes | Make a comparison between what do we have and what do we lack (according to the prepared list) | GDIPC/Regions/Clusters/ Hospitals | One month | [8 empty] | Head of Supplies | [12 empty] | M/E tools like a comparison list to track and check the availability of supplies all the time in all ICUs | Number of ICUs that have adequate supplies (Quantity & Quality) per Total number of ICUs observed x 100 |  |  | All Zones
|  | 2. No list of supplies & codes |  |  | Determine and analyze the shortage of supplies (level of shortage: MOH/ Regions/Hospitals) | How, when and why the shortage is occuring | GDIPC/Regions/Clusters/ Hospitals | Two months | bar: 2023 2 to 2023 3
|  | 3. Maldistribution of supplies |  |  | Communicate with the supply department ahead of time | Send requests officially through email to the supply department | GDIPC/Supply Dept | 2 days | bar: 2023 3
|  | 4. Inefficient supply chain operating system |  |  | Follow up the availability of supplies in every ICU (Short of supplies) | Create a mechanism of alarm and follow up (Tracking system- Manual/Electronic) | Hospitals | One month | [7 empty] | Supply Dept | bar: 2023 4
[5 empty] | Review the cycle of supply chain system and conduct quarterly meeting with the supply department. | Conduct a joined workshop of revision and corrections | GDIPC/Supply Dept | 2 Days | bar: 2024 1
[5 empty] | Have the supplies according to determined standards of quality | Put and follow standards of quality of the supplies | GDIPC | One month | bar: 2023 2
3 | Education & Training of Staff, Patients and Family | 1. Lack of knowledge on how to prevent CAUTI | To educate staff, patient and family members on the care and maintenance of urinary catheter. | 1. To include education and training of staff about the Prevention of CAUTI | Emphasize Prevention of CAUTI during in service education and training | In service education and training | Hospital | Continuous | [21 empty] | Lists of educated staff in CAUTI Prevention |  |  |  | All Zones
|  |  |  | 2. To orient the new staff on Prevention of CAUTI | Education of the staff using online modules | PDF copies online | Hospital
|  | 2. New staff orientation not including CAUTI Prevention |  |  | Reinforce orientation on CAUTI Prevention to newly hired staff in ICUs | New staff orientation | Hospital | [22 empty] | List of staff oriented in CAUTI Prevention
|  | 3. No education of patients and family members on how to take care of urinary catheters |  | 3. To educate conscious patient and family members on the care and maintenance of urinary catheter | Education of the conscious patients and family members on care and maintenance of urinary catheter | Brochures, leaflets | Hospital | [22 empty] | Brochures in place
|  | 4. No hands on training |  | 4. To provide hands on training to staff during in service lectures in ICU | Schedule hands on training of ICU staff in urinary catheter insertion and care to be included during in service lectures or workshop | Schedule of lectures or workshop for ICU staff | Hospital | [9 empty] | Interested companies | [13 empty] | Number of HCWs trained on CAUTI prevention / Total number of targeted HCWs * 100
[5 empty] | Make 2 videos on CAUTI prevention (Insertion and maintenance) | Video presentation on urinary catheter insertion and maintenance | GDIPC | [9 empty] | Interested companies
|  | 5. No CAUTI Champions in the unit to coach, educate and follow up CAUTI prevention practices |  | 5. To appoint CAUTI champions in the unit to be a role model or coach in prevention of CAUTI | Choose skilled staff to be CAUTI Champions in the unit | Appoint staff according to their skills and knowledge | Hospital
|  | 6. No awareness campaign for CAUTI prevention |  | 6. To Initiate awareness campaign on the prevention of CAUTI | Create posters and other educational materials to be posted in the units | Design & distribute posters | GDIPC/ Region/Clusters | 1 month | [21 empty] | Posters in place | bar: 2024 1; 2025 1
[6 empty] | Campaign materials | Region/Cluster/ Hospital | 1 month | bar: 2023 2; 2024 2; 2025 2
4 | CAUTI Prevention Best Practices | 1. No proper assessment on the reason for high CAUTI rates | To promote and standardize the knowledge and practice according to new and updated evidence-based recommendations for the prevention of catheter-associated urinary tract infection (CAUTI) for all of healthcare professionals in all healthcare settings. . | 1. To assess the current situation in the hospitals with high CAUTI rates by implementing Road map assessment | Prepare Roadmap assessment to identify the gaps | CAUTI Roadmap Assessment Form | GDIPC | 1 week | [25 empty] | Black Zones
[5 empty] | Share prepared Road Map Assessment Form to all 6 targeted hospitals in black zone initially |  | GDIPC | 1 week
[5 empty] | Analyzed the Road Map Asessment Form received from the 6 targeted hospitals in black zone |  | GDIPC | 1 week
[5 empty] | Share the results of the gap analysis in the 6 targeted hospitals in black zone with the domain members | Gap Analysis | GDIPC/Hospital/Region/Cluster | 1 week
[5 empty] | Prepare accordingly the suitable interventions addressing to the identified gaps |  | GDIPC | 1 week
[5 empty] | Follow up and monitor the needs identified from the gaps and give supportive measures | Supportive Action Plan | GDIPC/ Region/Clusters | continuous | [25 empty] | All Zones
|  | 2. Non compliance to CAUTI Prevention Guidelines and bundles of care |  | 2. To show decrease in CAUTI rates with the compliance to CAUTI prevention guidelines education and bundles of care | Create an evidence-based CAUTI Prevention Guidelines | MOH Guidelines | GDIPC | 1 week | [25 empty] | All Zones
[5 empty] | Review thoroughly the CAUTI Prevention Guidelines for implementation |  | GDIPC | 1 week
[5 empty] | Ask for approval for dessimination of PDF copies of CAUTI Prevention Guidelines |  | GDIPC | 1 week
[5 empty] | Dessiminate the PDF copies of approved CAUTI Guidelines | Emails | GDIPC/ Region/Clusters | 1 week
[5 empty] | Follow up implementation of the said Guidelines with the Regional Coordinators to include in their visits |  | GDIPC/ Region/Clusters | continuous
[5 empty] | Receive monthly compliance rates to CAUTI Prevention bundles from regional surveillance coordinators | Manual HAI Data Submission and/or HESN Plus | GDIPC/ Region/Clusters | Monthly
[5 empty] | Analyze the received compliance rates to CAUTI Prevention bundles |  | GDIPC | Monthly | [21 empty] | Compliance Rate to CAUTI Prevention bundles | No.of staff compliant to all elements of CAUTI Prevention bundles per total no. of observed staff x 100
[5 empty] | Create quarterly report in a dashboard to include compliance to education on CAUTI Guidelines and bundles | Dashboard | GDIPC | Quarterly
[5 empty] | Provide quarterly feedback to Regional Coordinators on the created reports | Quarterly Report | GDIPC | Quarterly
|  | 3. Non adherence to proper urinary catheter insertion |  |  | Do random audit on adherence to proper urinary catheter insertion | Adherence Monitoring Form on urinary catheter insertion | GDIPC/ Region/Clusters/Hospitals | continuous | [21 empty] | Adherence rate to urinary catheter insertion practices | Total no. of Yes observed urinary catheter insertion practices per total no of observed practices x 100
|  | 4. Non adherence to proper urinary catheter care and maintenance practices |  |  | Do random audit on adherence to proper urinary catheter care and maintennace practices | Adhrence Monitoring Form on Maintenance of urinary catheter | GDIPC/ Region/Clusters/Hospitals | continuous | [21 empty] | Adherence rate to urinary catheter maintenance practices | Total no. of Yes observed urinary catheter maintenance practices per total no of observed practices x100
|  | 5. Nursing staff not competent on handling urinary catheter |  | 3. To increase ICU staff competency in the insertion and maintenance of urinary catheter in national healthcare facilities | Create evidence- based Competency Assessment Checklist for insertion of indwelling urinary catheter | Competency assessment tool on insertion of urinary catheter | GDIPC | 1 week | [21 empty] | List of competent staff in insertion of urinary catheter | No. of competent staff in the unit per Total no.of staff assessed on insertion of urinary catheter x100
|  | 6. Physicians and/or nursing staff are incompetent in inserting urinary catheter |  |  | Create evidence- based Competency Assessment Checklist for maintenance of indwelling urinary catheter | Competency assessment tool on maintenance od urinary catheter | GDIPC | 1 week | [21 empty] | List of competent physicians and or nursing staff in the maintenance of urinary catheter | No. of competent staff in the unit per Total no.of staff assessed on maintenance of urinary catheter x 100
[5 empty] | Review and approve the created evidence- based Competency Assessment Checklist for insertion of indwelling urinary catheter |  | GDIPC | 1 week
[5 empty] | Dessiminate approved competency assessment for insertion and maintenance of urinary catheter to all regions | Emails | GDIPC | 1 week
[5 empty] | Enforce implementation of competency assessment on insertion and maintenance of urinary catheter for all concerned staff in adult medical surgical ICU in the regions | Memorandum | GDIPC/ Region/Clusters/Hospitals | continuous
[5 empty] | Monitor all targeted hospitals' compliance to Competency Assessment for insertion and maintenance of indwelling urinary catheter | Dashboard | GDIPC/ Region/Clusters/Hospitals | continuous
5 | CAUTI Surveillance and Data Management | 1. Under reporting and mis-identification of CAUTI Definitions |  | To collect, assess and analyze the CAUTI events, rates and its device utilization ratios | Impose to use CDC/NHSN criteria for identifying patients who have symptomatic and asymptomatic UTI | Surveillance Manual | GDIPC/Regions/Clusters/Hospitals | continuous | [25 empty] | All Zones
[5 empty] | Ask to perform surveillance for CAUTI and provide regular (e.g., quarterly) feedback of unit-specific CAUTI rates to nursing staff and other appropriate clinical care staff. | Feedback report of CAUTI | GDIPC/ Region/Clusters/Hospitals | continuous
|  | 2. CAUTI rates not monitored and calculated per hospital and region |  |  | Monitor hospital CAUTI rates and device utilization ratios | Manual data collection and/or HESN Plus | GDIPC/Regions/Clusters | continuous
[5 empty] | Collect, Calculate and Analyze the CAUTI rates |  | GDIPC | continuous | [21 empty] | CAUTI Rate | Total no.of CAUTI events per total no. of urinary catheter days x1000
[5 empty] | Collect, Calculate and Analyze the device utilization ratios |  | GDIPC | continuous | [21 empty] | Device Utilization Ratio | Total no. of urinary catheter days per total no. of patient days
|  | 3. National benchmark not specified for CAUTI |  |  | Set the benchmark to be used in the CAUTI Reduction Strategy | Manual data collection and/or HESN Plus | GDIPC | continuous
|  | 4. CAUTI rates not categorized per colour zones |  |  | Categorize the hospitas and regions' CAUTI rates and ratios according to colour zones |  | GDIPC | continuous
[5 empty] | Create a plan for interventions based on the colour zones | Intervention Plan per colour zones | GDIPC | continuous
6 | CAUTION to CAUTI (C2C) Initiative | 1. No rewards given for the efforts of HAI Reduction | To conduct CAUTIoN TO CAUTI (C2C) a one year competition among national healthcare facilities with champion release. | To be C2C (CAUTI Rate of 0.5 per 1000 urinary catheter days ) in all national healthcare facilities with Adult Medical Surgical ICUs | Finalize the required CAUTIoN to Cauti (C2C) Eligibility Criteria Checklists | Distribute eligibility criteria checklists to the selected hospitals | GDIPC | 1 month | [7 empty] | Regions/Clusters/ Hospitals | Internal Communication | [12 empty] | Eligibility criteria completed |  |  |  | ALL Zones
|  | 2. Not indicated insertation |  |  | Determine the baseline and requierments for C2C | Obtain the C2C hospitals' CAUTI rates through HESN Plus | GDIPC / Hospitals | Continuous | [21 empty] | Rate measurements | bar: 2023 2 to 2023 4
[5 empty] | Conduct a planning workshop with the CAUTIoN nominated hospitals and regions | Set the road map guidelines for the CAUTIoN workshop | GDIPC | 2 weeks | [21 empty] | Roadmap finalized
|  | 3. No CAUTI reduction supportive interventions from hospitals leadership |  |  | Conduct the C2C support visits using the Roadmap Assessment Form | Deliver technical advice to the CAUTIoN nominated hospitals | GDIPC | Continuous | bar: 2023 2 to 2023 4
[5 empty] | Hold evaluation process for assessing C2C components | Set dates and select the CAUTIoN evaluators for the final evaluation visits and exam | GDIPC | 2 days | [21 empty] | Evaluation workshop's report | bar: 2023 3
[6 empty] | Calculate the CAUTI rates and pick the winning hospitals with 0.5/1000 catheter days or less for a period of 10 months | GDIPC | continuous | [21 empty] | CAUTI Rate measurements | No. of C2C Hospitals who reached a CAUTI rate of 0.5 or less for a period of 10 months per total number of C2C hospitals in the competition | bar: 2023 2 to 2023 4
[5 empty] | Celebrate the completion of C2C Competition under the patronage of MOH leaders and high officials | Coordinate with the internal communication for the announcement of the winning hospitals | GDIPC / Hospitals | 1 week | [21 empty] | Announcement of Winners | bar: 2023 4
[6 empty] | Conduct an awarding ceremony for winners of CAUTIoN to CAUTI (C2C) Competition | GDIPC/Region/Cluster/Hospitals | 1 day | [21 empty] | Celebration day | bar: 2024 1
7 | Personnel and Communication Management | 1. No involvement of doctors and other multidisciplinary team in the prevention of CAUTI | To enhance engagement of multidisciplinary stakeholders helping CAUTIoN implementation | To impose a daily CAUTI rounds to check for urinary catheter indication and need for removal . | Create a Daily CAUTI Safety Huddle Form | Daily CAUTI Safety Huddle Form | GDIPC/Regions/Clusters/Hospitals | 1 week | [21 empty] | Compliance to Daily CAUTI Safety Huddle | No. of hospitals compliant to daily CAUTI safety huddle form per total number of targeted hospitals |  |  | All Zones
[5 empty] | Form a multidisciplinary team to do the daily pre-shift task of CAUTI Safety Huddle | Head of ICU will assign members of the CAUTI Safety Huddle | Hospitals | 2 days | bar: 2024 1; 2025 1
[5 empty] | Explain the CAUTI Safety Huddle process | Procedure of the Huddle | Hospitals | 1 day | [8 empty] | Hospital Directors | bar: 2024 1; 2025 1
[5 empty] | Implement the Daily CAUTI Safety Huddle in all targeted hospitals with Adult Medical Surgical ICU | Daily pre-shift CAUTI Safety Huddle must be done | Hospitals | Continuous
|  | 2. No internal communication tools in the workplace to promote CAUTI Prevention | To establish a channel of communication to disseminate the information and knowledge about CAUTIoN and share our strategic experience. | To have a clear plan for CAUTI Prevention regarding the communication channels that connect leaders, healthcare workers and other personnel to achieve the strategic goals. | Plan for communication for each hospital (written and documented plan) | Hospitals' Communication Plans | Hospitals | Continuous | [7 empty] | GDIPC | Regions/Clusters/Hospitals | [12 empty] | written communication plans | No of hospitals have communication plans per total number of targeted hospitals |  |  | All Zones
|  |  |  | To revise and enhance the current communication processes | Review the communication regarding CAUTI (detect weakness/rooms of improvements etc.) | Hospitals' Communication Set up | Hospitals | Continuous | [21 empty] | efficient and effective communication set ups | No of hospitals have efficient and effective communication set ups per total number of targeted hospitals
|  |  |  | Provide efficient and effective communication set up " internet, computers and others" | Establish communication set up in national healthcare facilities by provision of the needed equipment |  | Hospitals | Continuous
|  | 3. No experience sharing of MOH hospitals' success of the prevention of HAI | To make national healthcare facilities' success in Prevention of HAIs well known and considered globally | To participate in global healthcare exhibitions, conferences, seminars | Select famous global healthcare exhibitions | Exhibitions | GDIPC | Continuous | [7 empty] | GDIPC | [13 empty] | M/E Tools e.g Checklist |  |  |  | All Zones
[5 empty] | Prepare materials, speakers and representatives | Materials, Speakers, Representatives | GDIPC | Continuous
|  | 4. Lack of recognition for the efforts of GDIPC |  | To publish GDIPC success stories in the prevention of HAIs | GDIPC publications | Publications | GDIPC | Continuous
|  |  |  | To plan and propose projects and initiatives to involve reputable infection prevention and control bodies or organizations | Plans and proposals | written plans and proposals | GDIPC | 2 months | bar: 2024 1
8 | Performance Improvement by Monitoring & Evaluation | 1. No CAUTI performance improvement monitoring and evaluation on a regular basis | To frequently monitor and evaluate CAUTIoN KPIs, send reports to regions and when needed for the duration of the strategy. | To come out with a clear dashboard of CAUTI KPIs in national healthcare facilities. | Arrange a baseline data, a file and registry and keep records for CAUTI | Document all (8) CAUTIoN Strategy components' activities & achievements | GDIPC | Continuous | [7 empty] | M/E Tools | [13 empty] | M/E Tools eg D.Form | A fully - detailed dashboard of CAUTIoN KPIs and CAUTI rates presented at least quarterly for the three yaears' duration of the strategy |  |  | NA
[5 empty] | Set up a communication system and network | Encompasses all stakeholders, decision - makers, operators, IPs, directors and GDIPC personnel | GDIPC/Regions/Clusters/ Hospitals | Continuous | [21 empty] | Internal means of communication
[5 empty] | Conduct online lecture presentation on Performance Improvement Project | Online lecture presentation | GDIPC/Hospitals | 1 day / quarter | [21 empty] | 4 lecture-presentation completed | bar: 2023 2 to 2023 4
[5 empty] | Regulate and assess the progress of CAUTIoN Strategy in general and for each component | Internal Assessment Form | GDIPC | Continuous | [21 empty] | Assessment Form filled accordingly
[5 empty] | Share with the surveillance program in visiting (3) selected black - zone hospitals / ICUs for more KPIs improvement | Discuss and agree upon a unified and comprehensive plan of intervention | GDIPC | 2 weeks | [21 empty] | 3 Visits completed | bar: 2023 2 to 2023 3